|  |  | REPUBLIC OF ALBANIA MINISTRY OF EUROPEAN INTEGRATION |
| --- | --- | --- |

EUROPEAN TERRITORIAL COOPERATION

IPA CROSS-BORDER PROGRAMME “GREECE – ALBANIA” 2007-2013

PROGRAMME MANUAL

MARCH 2010

1ST  DRAFT

TABLE OF CONTENTS

1. Introduction	3

1.1 Abbreviations	3

1.2 Glossary	4

1.4 General Programme Information	8

2. Project Applicant’s Manual	13

2.1 How to develop a project idea/proposal	14

2.2. Main features of projects	17

2.2.1 Eligible Partnerships / The Lead Partner Principle	17

2.2.2 Eligibility of applicants: who may apply?	17

2.2.3 Eligibility of expenditure/Project Budget	23

2.2.3 Duration of Projects	27

2.3. Submission procedure	27

2. 5 Evaluation Procedure	51

3. Project Implementation Manual	54

3.1 Contracting of a Project Proposal	54

3.2 Reporting procedures	54

9. Payments / cash flows	62

3.4 Project modifications	63

3.5 FIRST LEVEL CONTROL	66

ANNEXES	67

I. PROJECT SELECTION CRITERIA	67

II. PARTNERSHIP AGREEMENT	67

III. CONTRACTS	67

IV. PROGRESS REPORT	67

# 1. Introduction

## 1.1 Abbreviations

| AA | Audit Authority |
| --- | --- |
| CA | Certifying Authority |
| CBC | Cross-Border cooperation |
| ETC | European Territorial Cooperation |
| IPA | Instrument for Pre-Accession Assistance |
| EU | European Union |
| EUD | Delegation of the European Union |
| FCC | Financial Control Committee |
| LP | Lead Partner |
| ICT | Information and Communication Technology |
| JTS | Joint Technical Secretariat |
| MA | Managing Authority |
| JMC | Joint Monitoring Committee |
| MCS | Management and Control Systems |
| NGO | Non-governmental Organization |
| NSRF | National Strategic Reference Framework |
| OLP | Overall Lead Partner (Lead Beneficiary) |
| OS | Operating Structure |
| PA | Priority Axis |
| PRAG | Practical Guide to Contract Procedures for EC External Actions |
| R&D | Research and Development |
| SME | Small & Medium Sized Enterprise |
| PP | Project Partner (Beneficiary) |

## 1.2 Glossary

Operational Programme (OP) – Document jointly drawn up and submitted by the participating countries according to Article 91 of Regulation (EC) No 718/2007 and adopted by the Commission decision  (EC) 4708/2008 of 05/09/2008

Managing Authority (MA) – Body designated by the participating countries, responsible for managing and implementing the cross-border programme in accordance with the principle of sound financial management, carrying out the functions set out in Article 103 of Regulation (EC) 718/2007.

Operating Structure (OS) – The OS co-operates closely with the Managing Authority in the programming and implementation of the relevant cross-border programmes establishing common co-ordination mechanisms. The OS is responsible for the implementation of the Programme according to Article 139 of Regulation (EC) No 718/2007.

European Union Delegation (EUD)- The Delegation of the European Union in Tirana represents the European Commission inside the country vis-à-vis the authorities and the general population. In the case of centralized Management of the IPA CBC Programme, the Delegation of the European Union acts as the Contracting Authority for Partners inside Albania.

Contracting Authority (CA)- An Authority legally responsible to sign contracts with a Project Lead Partner.  In the case of the present IPA CBC Programme the Managing Authority and the European Union Delegation (Tirana) will act as the Contracting Authorities for the partners of the two participating countries.

Joint Technical Secretariat (JTS) – The body set up by the MA after consultation with the Participating countries represented in the programme area, according to Article 102 Regulation (EC) 718/2007, to assist the Managing Authority and Joint Monitoring Committee, and when appropriate the Audit  Authority and Certifying Authority in carrying out their respective duties.

Beneficiary – Bodies invited to submit proposals.  Eligible beneficiaries are specified in each call for proposals.

Project Partners (PPs) - Partners participating in an operation/project, that correspond to the term "beneficiary" used in Article 96 of Regulation (EC) 718/2007.

Joint Monitoring Committee (JMC) – The body set up by the participating countries to ensure the overall effectiveness and quality of the implementation of the cross-border programme according to Article 110 of Regulation (EC) No 718/2007.

Joint Steering Committee (JSC) - The committee established to support the Joint Monitoring Committee, in fulfilling its tasks, with regard to the selection of projects according to Article 110, paragraph 5(f) of Regulation (EC) No 718/2007

Certifying Authority (CA) – National, regional or local public authority or body, designated by the Member State for certifying statements of expenditure and applications for payment before being sent to the Commission. In this context, the CA shall carry out the functions envisaged in Article 104 of Regulation (EC) 718/2007..

Audit Authority (AA) – The institution responsible for verifying the effective functioning of the management and control system of the operational programmes. In this context, the AA shall be responsible for carrying out the functions envisaged in Article 105 of Regulation (EC) 718/2007 and may be assisted by a Group of Auditors (GoA) comprising of a representative from each partner state in the Programming Document.

Controllers – Greece shall designate the controllers responsible for verifying the legality and regularity of the expenditure declared by final beneficiaries in Greece participating in the operation, according to Article 108 of Regulation (EC) 718/2007. The DEU will be responsible for the first level control regarding the expenditure declared by the beneficiaries from Albania.

Project/Operation/Action - A project selected by the Joint Monitoring Committee (or Steering Committee), according to the selection criteria approved by the Joint Monitoring Committee, and implemented by the project partners.  Each project contributes to the achievement of the goals of the priority axis under which it is submitted.

Management Information System (MIS) – The management system for recording and storing in computerised form accounting records for each operation under the operational programme.

EU contribution: the part of the eligible expenditure of a project which is financed by the European Union.

National Co-financing – The non-EU contribution to the projects’ budget provided by either the State budget of each participating country or provided as Own Contribution by the Project Partners.

Irregularity - any infringement of a provision of a European Union’s law resulting from an act or omission by an economic operator which has, or would have, the effect of prejudicing the general budget of the European Union by charging an unjustified item of expenditure to the general budget.

Financial Correction – The cancellation of all or part of the National and European Union’s  contribution to an operation, in the context of its co-financing by the OPs, which is similar to the detected irregularity.

Amount unduly paid – All expenditure not representing an equal value of delivered products or services, according to the expenditure terms of the Subsidy Contract.

Recovery – The repayment by the beneficiary of amounts unduly paid as a result of no legal cause.

1.3  Purpose

The purpose of this Programme Manual is to serve as an essential reference document for all bodies interested in: a. applying for funding under the “Greece-Albania IPA cross-border Programme” 2007-2013 (hereinafter the Programme) and  b. implementing a project which has been selected for funding. Since this Programme reference guide involves also details relevant to the present call for proposals, the reader should take into account only the version of the Manual accompanying the specific Call (the manual will be updated accordingly if changes occur through the different Calls for Proposals).This manual, together with the programme’s website www.interreg.gr, as well as the sites of the Operating Structure www.mie.gov.al and of the Delegation of the European Union  to Tirana, http://ec.europa.eu/delegations/albania/index_en.htm, will provide practical information and assistance to potential applicants, in order to prepare and submit a project proposal or to successfully implement an approved project.

Applicants should therefore study the entire manual carefully. The Manual consists of three parts:

- Introduction - General Information for the Programme

- The Project Applicant’s Manual

- The Project Implementation Manual

NOTE:

This manual relates to the present management mode of the program:

- Transitional arrangements according to Art 99 of Regulation (EC) 718/2007

- Centralised management in Albania

## 1.4 General Programme Information

Cross border cooperation policy is about establishing links across national boundaries to enable joint approaches to common problems and opportunities. The present Programme constitutes actually a set of proposals for the interventions envisaged under the terms of the cross border cooperation of European Territorial Cooperation for the period 2007-2013. The “Greece – Albania IPA Cross-Border Programme” has been approved by the Commission Decision No. EC(2008) 4078 on 5/9/2008.  As the successor to the “Neighbourhood programme Greece – Albania” that operated between the two countries the period 2000 - 2006, it will attempt to capitalize on the experience gained and the lessons learned by both the participants and the implementing structures in order to bring cooperation to a new level.

The global objective of the programme is to increase the standard of living of the population by promoting sustainable local development in the cross-border area.

Within this framework, the priorities which constitute the policy outline for the convergence in the area of intervention of the specific Programme are:

Priority 1: Enhancement of cross-border economic development

Priority 2: Promotion and development of the environment and natural and cultural resources

Priority Axis 1 will be implemented by four Measures focusing on:

- the promotion of entrepreneurship,

- the promotion of sustainable tourism

- People to people actions

- facilitation of border accessibility through small-scale infrastructure

Priority Axis 2 will be implemented by two Measures focusing on

- the promotion and protection of environmental resources and

- the promotion and protection of the natural and cultural heritage of the area.

The programme strategy is described in detail in the Programming Document of the “Greece – Albania IPA Cross-Border Programme” 2007-2013.

What is the area of the Programme?

The eligible area of the programme, as illustrated in the map below, comprises of six Prefectures on the Greek side (Florina, Kastoria, Ioannina, Thesprotia, Kerkira and Grevena – the last one as an adjacent area) and three Districts on the side  of the Albania (Vlorë, Gjirokastër  and Korçë), covering an area of 21.588 km2 and 1.040.118  inhabitants.

Eligible area

The programme covers the following eligible areas:

Eligible NUTS III or equivalent regions

| Country | Prefecture/District |
| --- | --- |
| GREECE | Prefecture of Ioannina |
|  | Prefecture of Thesprotia |
|  | Prefecture of Florina |
|  | Prefecture of Kastoria |
|  | Prefecture of Kerkira |
| ALBANIA | District of Gjirokastër |
|  | District of Korçë |
|  | District of Vlorë |

Eligible adjacent areas

| Country | Prefecture/District |
| --- | --- |
| GREECE | Prefecture of Grevena |

Adjacent area

Based on the flexibility rule provided by Article 97 of Regulation (EC) 718/2007, Grevena Prefecture in Greece (NUTS II) is included in the Programme as adjacent area. The adjacent area has been selected to maximise the impact of cross border cooperation programmes’ achievements. According to Article 97 of Regulation (EC) 718/2007, these areas combined can receive up to 20% of the EU contribution to the cross-border programme. This means in practice that the programme may report costs related to the activities incurred on the territory of these areas to the limit of 20% of the EU contribution to the cross-border Programme budget.

However, this does not mean that a fixed share of 20% of the EU contribution to the cross-border programme budget is reserved for partners from these areas. The cross border added value of participation of partners from these areas will be assessed on a project by project basis.

Programme funding

The Programme budget allocated for the period 2007-209 is € 10.246.220.   This amount consists of € 8.153.676 EU contribution and € 2.092.544    national contributions.  The national co-financing rates for Greece and for the Albania are respectively 25% and 15%.   For the 1st Call for Project proposals, for the project partners from the Albania, the 15% of the national co-financing will be covered by the beneficiaries’ own funds.

Programme Management – Implementation

In line with Article 99 of the Commission Regulation (EC) No 718/2007 of 12 June 2007 implementing Council Regulation (EC) No 1085/2006 establishing an instrument for pre-accession assistance (IPA) the “Greece-Albania IPA Cross-border Programme” is going to be implemented under the transitional arrangements. The programme may be converted during the programming period into a shared management if agreed by the participating countries and the European Commission.

The structures of the programme are:

The Managing Authority (MA), responsible for managing and implementing the Cross-border Programme in accordance with the principle of sound financial management and for carrying out the functions set out in Article 103 of Regulation (EC) No 718/2007.  The Managing Authority of European Territorial Cooperation Programmes at the Ministry of Economy, Competitiveness and Shipping in Thessaloniki, Greece is designated as the Managing Authority of the IPA Cross-border Programmes.

The Certifying Authority (CA), responsible for certifying statements of expenditure and applications for payment before being sent to the Commission as well as for receiving payments from the Commission and making payments to the Lead Partner in Greece (lead beneficiary), according to Article 104 of Regulation (EC) 718/2007.  The Paying Authority for the CSF, the Community Initiatives and the Cohesion Fund at the Ministry of Economy, Competitiveness and Shipping, Greece is designated as the Certifying Authority of the IPA Cross-border Programmes.

The Audit Authority, responsible for verifying the effective functioning of the management and control system of the operational programme, according to Article 105 of Regulation (EC) 718/2007. The Financial Audit Committee (EDEL) at the Ministry of Economy Competitiveness and Shipping – Secretariat General for Fiscal Policy (General Accounts of the State) is designated as the Audit Authority for the IPA Cross-border Programme.

The Audit Authority of the programme may be assisted by a Group of Auditors comprising of a representative from each Country participating in the operational programme.  However, as this programme is implemented under the transitional arrangements and the Audit Authority will be responsible only for expenditure within Greece, a Group of Auditors is not required in this case. Nevertheless, such a Group may be established in order to ensure an appropriate exchange of information and good practice between the participating countries.

The Joint Monitoring Committee (JMC), comprising representatives of the two participating countries at an equal basis, in order to comply with the partnership principle in managing, monitoring and evaluating the operations, satisfies itself as to the effectiveness and quality of the implementation of the cross-border programme according to Article 110 of Regulation (EC) No 718/2007.

The Joint Steering Committee (JSC), supports the Joint Monitoring Committee, in fulfilling its tasks, with regard to the selection of projects according to Article 110, paragraph 5(f) of Regulation (EC) No 718/2007 on the basis of the preliminary technical evaluation, carried out by the JTS, with possible support by external experts (assesors) if needed.

The Joint Technical Secretariat, assisting the Managing Authority, National Authority / Operating Structure, the Joint Monitoring Committee and the Joint Steering Committee and when appropriate the Audit Authority and Certifying Authority in carrying out their respective duties in line with Article 102 Regulation (EC) 718/2007,

The Operating Structure is responsible for implementing the part of the Programme concerning Albania.  During centralized management in Albania the Operating Structure is the Ministry of European Integration. The responsibilities of the Ministry of European Integration as Operating Structure are defined in Article 139 of Regulation (EC) No 718/2007.

The Contracting Authority is legally responsible to sign contracts with a Project Lead Partner.  In the case of the present IPA CBC Programme the Managing Authority and the European Union Delegation (Tirana) will act as the Contracting Authorities for the partners of the two participating countries.

# 2. Project Applicant’s Manual

The Project Applicant’s manual includes information about:

- The development of a project idea/proposal;

- The submission procedure;

- Main features of projects;

- Filling in the Application Form.

It is recommended that those interested in submitting a proposal under the Programme, examine carefully - besides the present manual - the  “Greece – Albania IPA Cross-Border Programme” which is available on the website of the Managing Authority (MA) at www.interreg.gr as well as on the sites of the Albanian Operating Structure www.mie.gov.al and of the Delegation of the European Union to Albania, http://ec.europa.eu/delegations/albania/index_en.htm.

Moreover, interested parties may contact the persons appointed by the MA and the OS to get support in designing their proposals in accordance with the strategic aims of the Programme.

This Project Applicants’ Manual describes the contents of the Applicant’s Package published in the framework of the first Call for Proposals of the  “Greece - Albania IPA cross-border Programme” 2007-2013.

The Applicant’s Package consists of the following documents:

  - Announcement of the Call for Proposals

  - Application Form

  - Partnership Declaration-Co Financing Statement

  - Declaration of not generating revenues

  - Specification of Budget Costs (one for each Lead Partner)

  - Declaration by the Lead Partner in Albania

  - Legal Entity Form (for the Lead Partner in Albania)

  - Financial Identification Form (for the Lead Partner in Albania)

  - Activity Brake-Up Table (for the Lead Partner in Albania)

The original application package is provided only in electronic form at the Managing Authority’s website www.interreg.gr.

## 2.1 How to develop a project idea/proposal

How to develop a project?

The following chapter provides to potential applicants the essential information that they need in order to start developing project ideas and partnerships.  It also describes the fundamental requirements which have to be met form the basis of each project proposal.

It should be noted that the programme finances joint projects which are jointly selected by the participating countries following calls for proposals that cover the entire eligible area.

Do you have an idea for a cross border project?

Project development is the phase in which an idea is translated into specific objectives and activities and is presented as a proposal. The starting point in defining a project idea is to identify the need. At the idea stage, every project developer needs to combine programme’s priorities with what regions on both sides really need.

In this sense,

- Programming document: The Programming Document includes a detailed analysis of the strengths and weaknesses of the programme area as well as the types of actions that the programme will finance. Try to assess how the project idea fits into the programme context through carefully studying its priorities and indicative interventions. Therefore, a careful study of the programme document as well as of other strategic documents (national and/or regional development plans, specific local policies, other field-specific strategies or guidelines etc.) is crucial for the applicants in developing good project ideas.

- Needs assessment: A background assessment of needs with particular focus on the target groups will definitely support project design.

- Stakeholders: Involve key stakeholders. Their views – as end users of the project’ products – may contribute to further develop the project idea given that they have crucial role in using the results of the project.

- Target groups:  A background assessment of target group needs with focus on the direct involvement  during the project preparation, that will definitely support project design and reach the objectives of the project and Programme in general

- Final Beneficiaries – A background assessment of the final beneficiaries needs with focus on the direct involvement during the project preparation, that will definitely support project design and reach the objectives of the project and Programme in general.

! Over time and with the input of partners the idea will be developed to include activities and objectives.

What makes a “good partner”?

Finding partners is not the difficult part in developing a partnership. Finding the right partners is the main challenge. With the right ones involved in a cross-border partnership, a project idea - documented in a clear and simple way - can be turned into a unified set of actions well targeted to the identified needs.

The development of a partnership is not an easy task as - before it becomes solid and efficient - it involves a number of stages such as:

- Identifying the partners, meeting them and learning about their interests, needs and skills. Make a choice based on their experience; their knowledge and specialisation of the chosen field, their complementarity which will support and guarantee exchange of know how, their needs, their commitment even from the very first steps of project generation and development. Face to face meetings prove to be of a great benefit.

- Communicating the project idea. Make a structured presentation to potential partners and to key stakeholders to help them understand the purpose, objectives, activities and context. Let them assess and decide whether they want to get involved.

- Challenging them by letting them shape the objectives and the expected results so as to reflect their own needs. Consultation with partners is crucial given that their early involvement in the design of the project will ensure that it will be based on joint/common needs, skills and interests.

- Defining actions and allocating responsibilities to meet joint objectives. Be flexible to negotiate with all partners, their roles and responsibilities. Ensure common understanding, ownership and commitment. Realistic and achievable project plan increases partners’ commitment. Identify what each partner brings to the project and what expects to get form it.

The right time to involve potential partners to the development of a project idea is as soon as possible, given that the project should be a combination of needs and contributions of all the partners involved. Participating in a cross border cooperation project implies that the project idea reflects the needs of all partners.

! Be careful: check the rules on participation and eligibility before approaching partners.

How to define the content?

Do not forget that Programme requirements and the project idea have to be in line. There is no point in developing a project if it does not fit in the Programme. Projects need to collaborate on cross border activities that directly relate to addressing the priorities and objectives as set out in the Programming Document.

Steps to follow:

- The project needs to strongly demonstrate its cross border focus and show the true spirit of collaboration, through at least one of the following ways of cooperation: joint development, joint implementation, joint staffing and joint financing. However, it should be noted that, generally, projects are encouraged to cooperate by fulfilling all four of them. Keep in mind that the aim of cross border cooperation is to integrate areas divided by national borders that face common problems requiring common solutions.

- The project should complement and not duplicate other projects being carried out in the Programme area. Follow-up on projects financed by previous INTERREG / CARDS / Neighbourhood programmes is not enough. Projects need to show how they build on past experiences by bringing in something new.

- The project has to be realistic rather than attractive. Set the objectives as concrete, as quantifiable and realistic as they could be.

- Map out how objectives could be realized through a detailed action plan. The more precisely the goals are formulated, the more effectively the project runs.

- Demonstrate common added value. In practice this means that the issue addressed is of such a nature that it cannot be satisfactorily tackled within one nation only and that cooperation improves the quality of results compared to the possible achievements of a partner working alone. Results can also be of relevance to the wider cooperation area and can potentially be transferred to other parts of the region.

- Have a regular contact with Programme management structures – Managing Authority and/or Operating Structure and/or Joint Technical Secretariat for clarifications on Programme priorities/objectives/activities.

! Keep in mind that a cross border partnership is not enough: ideas and activities must have a cross-border value too.

## 2.2. Eligibility

### 2.2.1 Eligible Partnerships / The Lead Partner Principle

Project proposals must include at least one partner from the Programme area (eligible and adjacent) of each country participating in the Programme.  The total number of partners on both sides of the border must not exceed five (5) including the Lead Partners.

Partners shall cooperate in at least one of the following ways: joint development, joint implementation, joint staffing and joint financing.

### 2.2.2 Eligibility of partners: who may apply?

This call for proposals is addressed to:

a. national, regional or local public authorities;

b. bodies governed by public law, having legal personality, other than legal entities defined under paragraph a, established for the specific purpose of meeting needs in the general interest (not having an industrial or commercial character) and which fulfil at least one of the following conditions:

- be financed, for the most part, by the national, regional or local authorities, or other bodies governed by public law or

- be subject to management supervision by those bodies or

- have an administrative, managerial or supervisory board, more than half of whose members are appointed by the national, regional or local authorities, or by other bodies governed by public law;

c. private organizations: non profit organizations founded according to applicable legal framework/law in the respective country can be eligible under the following conditions:

- they do not have a commercial or industrial character or activities

- they are non- profit and have a legal  personality.

- they are operational for at least 12 months before the launch of the specific call for  proposals. If a private organization is participating through a Branch located at the eligible programme area, the branch shall operate at least for one year before the launch of the specific call for proposals.

All projects shall be developed and managed according to the Lead Partner Principle (see below for details).

! In order to be considered eligible for funding, all the above actors should ensure that they are able to provide national co-financing. For partners from Albania, the national co-financing component must be covered by own funds.

The managerial adequacy of partners will be examined through the Project Selection Criteria.

Potential applicants from Albania may not participate in calls for proposals or be awarded grants if they are in any of the situations which are listed in Section 2.3.3 of the Practical Guide to contract procedures for EC external actions (available from the following Internet address:

http://ec.europa.eu/europeaid/work/procedures/implementation/index_en.htm)

The Lead Partner Principle

General

All projects within the framework of the European Territorial Cooperation will be developed and managed according to the Lead Partner Principle, the aim of which is to ensure genuine cooperation of all involved parties, by building it into the partnership structure.

Projects implemented under the Lead Partner Principle, generally, require a longer project development phase to establish the partnership and to decide upon the roles in project implementation and the budget allocation between partners.

To meet the special requirements of the “Greece-Albania IPA Cross-border Programme”, the Lead Partners Principle shall apply as described bellow:

a. Lead Partners

As outlined in art. 96 of Regulation (EC) 718/2007 implementing Council Regulation (EC) No 1085/2006 establishing an instrument for pre-accession assistance (IPA) and the COMMISSION REGULATION (EU) No 80/2010 of 28 January 2010 amending Regulation (EC) No 718/2007, two Lead Partners will be designated.  These partners must be directly responsible for the preparation and management of the action with their partners, not acting as an intermediary.

Beneficiaries from Greece shall appoint a  Lead Partner among themselves prior to the submission of the proposal. In case of approval, the Lead Partner in Greece will sign a Subsidy Contract (Subsidy Contract A) with the Managing Authority. Equally, the Beneficiaries from the Albania shall appoint a Lead Partner from Albania among themselves prior to the submission of the proposal for the project. In case of approval, the Lead Partner from the Albania will sign a Subsidy Contract (Subsidy Contract B or Grant Contract) with the Delegation of the European Union to Albania.

Each of the two Lead Partners shall assume the following responsibilities:

(i) it shall lay down the arrangements for its relations with the partners participating in the part of the operation taking place in the respective country  in an agreement comprising, inter alia, provisions guaranteeing the sound financial management of the funds allocated to the operation, including the arrangements for recovering amounts unduly paid;

(ii) it shall be responsible for ensuring the implementation of the operation in the

respective participating country;

(iii) it shall be responsible for transferring the European Union’s contribution to the partners participating in the operation, of the respective participating country;

(iv) it shall ensure that the expenditure presented by the beneficiaries participating in the part of the action taking place in the respective country has been paid for the purpose of implementing the operation and corresponds to the activities agreed between those partners;

(v) In addition to the above, the Lead Partners from Greece shall verify that the expenditure presented by the beneficiaries participating in the operation has been validated by the controllers.  In the case of the Lead partners from the Albania the Delegation of the European Union will be in charge for verifying the legality and regularity of the expenditure.

b. Overall Lead Partner (Applicant)

One of the two Lead Partners shall undertake the role of the “Overall Lead Partner” of the cross-border project.

This Overall Lead Partner shall assume the following responsibilities:

- It shall be directly responsible for the preparation and management of the entire project, not acting as an intermediary

- It shall ensure the sound implementation of the entire project;

- It shall submit to the JTS progress reports on the implementation of the entire project, based on the data that it receives from all partners.

- It shall record and store copies of the project documents (to allow for potential Financial Audits by DG Enlarg for the partners in Albania)

- It shall provide the MA/JTS and the Delegation of European Union in Albania with all monitoring data required;

- It shall act as the contact point with the Programme Management Bodies (Managing Authority, Delegation of European Union in Albania, Joint Technical Secretariat, etc.) for monitoring, reporting and general information purposes.

The Overall Lead Partner will sign an Overall Contract with the Managing Authority regulating the overall partnership reporting obligations to the MA..

! The Overall Lead Partner have to: - be established in the respective participating beneficiary country. - be operational for at least 12 months before the launching of the call for proposals.

The Lead Partners have to be established, registered or accredited in the respective countries i.e. the organization should be established by or accredited under an instrument governed by the internal law of the respective country for at least 12 months before the launching of this call for proposals. If is participating through a Branch located at the Programme area of non Member State, the branch should have been established and operating at least for 12 months before the date of the launch of the specific call for proposals.

c. Project Partners

All partners will cooperate for the implementation of the project by carrying out the activities assigned to them in the approved application. The partners should co-operate in at least one of the four possible ways described in the following section (Partners’ Cooperation). The expenses generated are eligible in the same way as those incurred by the Overall Lead Partner. They must, therefore, satisfy the same eligibility criteria as the ones applicable for the Lead Partner.

Indicatively, the partners’ responsibilities are to:

- Ensure the implementation of the project activities under their responsibility according to the project plan, the Partnership Agreement and the relevant contracts signed by the Project Lead Partners;

- Cooperate with the other project partners in the implementation of the project, the reporting and monitoring as deemed necessary; Key project conclusions, changes to project strategy and other important decisions should be made jointly;

- Prepare and submit to the Overall Lead Partner financial / progress reports, including the supporting documentation required (according to the official Progress report Templates provided). Partners from Albania should refer to the reporting requirements and obligations for the relevant supporting documentation described in Articles 2 and 15, of the General Conditions of the Grant Contract

- Assume responsibility in the event of any irregularity in the expenditure they have declared, and repay the Lead Partner of their country the amounts unduly received.  In case that the Lead Partner does not succeed in securing repayment from a project partner, the participating country on whose territory the relevant partner is located, shall reimburse the competent Authority (Certifying Authority for Greece, Delegation of European Union to Albania in the case of centralized management) the amount unduly paid to that partner.

- Be responsible for information and communications measures to the public.

Partners cooperation

The total number of partners must not exceed five (5) including the Lead Partners.

! Project partners should co-operate in at least one of the following ways:

1. Joint development

- All partners should contribute to the development of the project;

- Partners should define how the project will operate, i.e. joint development of objectives and outcomes, budget, timing and responsibilities for work packages and tasks to achieve the objectives;

- Partners should identify knowledge and experience that each one of them brings to the project, as well as what each partner expects to get from the project.

2. Joint implementation

- The Overall Lead Partner should bear the overall responsibility for the project. All partners should undertake responsibilities for different parts of the implementation.

- Each project partner responsible for a work package should coordinate and ensure that planned activities are carried out, interim targets are met and unexpected challenges to implementation are dealt with.

- Several partners may contribute to each work package.

3. Joint staffing

- All project partners should have a defined role and allocate staff to fulfill this role.

- Staff members should coordinate their activities with others involved in the activity or work package and exchange information regularly.

- There should be no unnecessary duplication of functions in different partner organizations.

4. Joint financing

- The project should have a joint budget with funding allocated to partners according to the activities they are carrying out (the budget split should reflect partner responsibilities).

- The budget should include annual spending targets and spending targets per work package.

- In general, all partners should contribute with co-financing.

Partnership Declaration & Partnership Agreement

The cooperation between the Overall Lead Partner, the Lead Partners  and the Project Partners are defined in the Partnership Declaration and, in more detail, in the Partnership Agreement.

The former is drafted at the stage of the submission of the project proposal and the latter at the stage of implementation of a project, which has been selected for funding. The Partnership Declaration also includes the co-financing statements as well as the declarations for non-double funding to be signed by all partners. For more details on the Partnership Declaration and the Partnership Agreement, please refer to the Applicant’s Package and Annex I of this manual.

Contractual arrangements

The relevant contracts to be signed, upon approval of a project proposal, shall determine the rights and responsibilities of the aforementioned parties. They shall describe the scope of activities to be carried out, the terms of funding, the requirements for reporting and financial controls, etc.

The following contracts shall be signed:

1. The Subsidy Contract A shall be signed between the Managing Authority and the Lead Partner from Greece, and it shall describe the responsibilities of the specific Lead Partner vis-a-vis the MA.

2. A Grant Contract (Subsidy Contract B) shall be signed between the Lead Partner from Albania and the Delegation of European Union in Tirana, which shall describe the responsibilities of the Lead Partner from Albania. The standard Grant Contract and its annexes is attached to this pack and can be found at http://ec.europa.eu/europeaid/work/procedures/implementation/index_en.htm.

3. A Contract shall also be signed by the Managing Authority and the Overall Lead Partner, regardless of its location, to describe the responsibilities of the latter.

### 2.2.3 Eligibility of expenditure/Project Budget

Project Budget

The projects’ permissible budget limits shall be specified in specific Call for proposals.

Eligible Categories of Expenditure of the Programme:

- Staff costs: Costs of Personnel executing tasks corresponding to the specific activities and deliverables of the project proposal.

- Overheads: These costs cannot exceed 7% of the Project’s Budget (Total direct eligible costs) and shall be eligible if they are based on real costs which relate to the implementation of the project and if they are charged to the project proportionately based on a fair and duly justified distribution method.

- Travel and Accommodation: This budget category includes all the expenses of the project’s beneficiary for the travel and accommodation costs of the personnel involved in the project, under the condition that these expenses are directly related to the activities of the project.  Travel and Accommodation costs involve:

- Costs related to the organisation (or participation) of meetings, seminars, conferences etc.;

- Costs, related to the research of a specific field or other similar activities, are eligible under this category and they must be distinctly mentioned in the activities of the project proposal.

- Travel and Accommodation outside of the programme area is considered eligible only if it is foreseen in the project proposal and approved;

  - External Expertise and services: Costs paid on the basis of contracts and against invoices to external service providers who are sub-contracted to carry out certain tasks of the project.

  - Equipment:  Costs for the purchasing of equipment with the condition that:

- Equipment is necessary for the project implementation and is foreseen in the approved application form;

- Suppliers should be selected, in the case of Greece, according to the rules of the relevant National Public Procurement Law; in the case of Albania according to Annex IV of the Grant contract to be signed between the EU Delegation and the Lead Partner from Albania.

- Investments/Infrastructure: Expenditure for Investments / Infrastructure with the condition that the cross- border impact of the investment is demonstrated and the activity is approved in the application form. The contractors of investments should be selected, in the case of Greece, according to the rules of the relevant National Public Procurement Law; in the case of Albania,  according to Annex IV of the Grant contract to be signed between the EU Delegation and the  Lead Partner from Albania. In each case, the contractor cannot be a partner in the project.

- Other: Direct general costs that can be attributed specifically to the project.

General Eligibility Criteria

Legal Framework

- Commission Regulation (EU) No 80/2010 of 28 January 2010 amending Regulation (EC) No 718/2007 implementing Council Regulation (EC) No 1085/2006 establishing an instrument for pre-accession assistance (IPA)e

- IPA 2007/2008/2009 Financing Agreements for 2007/08/09 signed by the Government of Albania and the Commission of European Communities

- National Eligibility Rules of Greece, as in force

- National Eligibility Rules of Albania, as in force

Preparation Costs

Costs within the budget lines staff costs, travel and accommodation costs and external expertise and services, which have been incurred for the preparation of the project are eligible for funding in accordance with the following conditions:

- If they have been incurred by the Partner in Greece, after the date of approval of the Programme and before the date of submission of the Application Form;

- For partners from Albania, grants may, as a rule, only cover costs incurred after the date on which the grant contract are signed. However, according to the provisions in PRAG, chapter 6 “Grants”, section 6.2.8 “Non retroactivity”, a grant may be awarded for an action which has already begun only where the applicant can demonstrate the need to start the action before the contract is signed (e.g. participation on kick-off meetings, organized by the Overall Lead Partner). In such cases, expenditure incurred, following a request in writing by the  Lead Partner from Albania and subsequent approval of the Delegation of European Union as Contracting Authority might be eligible

- If they show direct connection to the proposed project and are included in the application form;

- If they do not exceed the amount of 20.000€.

The following preparation costs are eligible:

- external expertise costs and/ or staff costs for the preparation of the application documents;

- joint meetings for the preparation of the project;

- travelling expenses directly related to joint meetings, including participation at the Lead Applicant’s seminar;

- cost analysis and preparatory research reports for the project activities

Overheads are not eligible under preparation costs.

As a general rule, costs shall be eligible for funding if:

- they have been incurred and paid out within the time frame in which expenditure can take place; The final date of eligibility of expenditure for Partners in Greece may not exceed 31/12/2016 under no circumstances.  Concerning Partners from Albania the costs must be incurred during the implementation period of the action as specified in Article 2 of the Special Conditions to the grant contract with the exception of costs relating to final reports, expenditure verification and evaluation of the action, whatever the time of actual disbursement by the Lead Partner and/or its partners.  The duration of the contract might be different than that of the Lead Partners in Greece, The implementation period can anyhow not be longer than 31/12/2013.

- they are directly related to the project either for the development or implementation of the project and they are planned in the approved project budget;

- they follow the “real cost” principle; costs which have been actually incurred and paid by the project beneficiaries and they can be supported by original invoices or other accounting documents of equivalent probative value;

- they have been incurred in the programme area of the “Greece – Albania IPA Cross-border Programme 2007-2013”

- they are in line with national and EU rules

- must be indicated in the estimated overall budget of the action,

- must be necessary for the implementation of the action which is the subject of the grant,

- they are identifiable and verifiable, in particular being recorded in the accounting records of the beneficiary and determined according to the applicable accounting standards of the country where the beneficiary is established and according to the usual cost accounting practices of the beneficiary,

- must be reasonable, justified and comply with the requirements of sound financial management, in particular regarding economy and efficiency.

Detailed information about the eligibility of expenditure per country will be available at the ‘Programme Eligibility Rules’ and the ‘Verifications Manual’ that will be published at the web sites of the Managing Authority, the Delegation, and the Operating Structure.

### 2.2.3 Duration of Projects

The permissible duration of projects shall be specified in each Announcement of Call for proposals.

## 2.3. Submission procedure

A Project Proposal consists of:

- the ‘Application Form’ (standard excel form provided)

- the ‘Partnership Declaration’ (standard form provided)

- ‘The Declaration of not generating revenues’ (standard form provided). In case of revenue generating projects, a cost - benefit analysis should be attached (using the  “Guide to cost-benefit analysis of investment projects Published by DG Regional Policy in 2008” available at http://ec.europa.eu/regional_policy/sources/docoffic/working/sf2000_en.htm )

- The ‘Specification of Budget Costs’, completed by both Lead Partners, one for each country  (a standard form provided)

- a. For bodies governed by public law (of article 2.2.2.b above) official documents providing evidence that the requirements of article 2.2.2.b of this call are met. In case that the nature of public body is not clearly delivered from the submitted documents, the JTS or MA may request additional documentation for clarification.

  - For private organisations (of article 2.2.2.c above) :

    - Statutes including all modifications.

    - Official document indicating the composition of the administrative/managerial or supervisory board.

    - Official document indicating the supervision by national, regional or local authorities, or other bodies governed by public law (if applicable)

    - Official document indicating the sources of the body’s revenues, during the last three years preceding the presentation of the project proposal.

    - Official Document providing proof for the non distribution of profits or declaration for the non distribution of profits if the first is not applicable.

    - Any official document certified by a public administration authority, providing that the organisation operates for at least one year before the launch of the specific call for proposals.

- A CD/DVD-ROM including the electronic version of the proposal as described at the Programme Manual (Part A. Applicant’s Manual).

- Infrastructure Projects must include the relevant accompanying documents (licenses, approval of feasibility study , building permits, preliminary designs, priced bill of quantities, technical specifications, environmental impact assessment etc., where applicable) proving the maturity of the proposed project.  All necessary licenses may be provided at a later stage, but before the signing of the subsidy contract

- The Lead Partner in Albania must submit the ‘Declaration by the Lead Partner in Albania (standard form provided)

- Lead Partners in Albania must submit

9a. The ‘Legal Entity Form’ (standard form provided)

9b. The ‘Financial Identification Form’ (standard form provided)

9c. The Activity Break-Up Table (standard form provided)

Partners from Albania may refer to the Practical Guide to Contract Procedures for EC External Actions (PRAG) for further guidance on filling the above documents (8 and 9).

As described in the Practical Guide to Contract Procedures for EC External Actions (PRAG), Guidelines for Applicants, partners from Albania should take into account the following:

The Legal Entity Sheet must be duly completed and signed by the Lead Partner in Albania, accompanied by the justifying documents which are requested therein. If the Lead Partner in Albania has already signed a contract with the Contracting Authority (the EU Delegation), instead of the legal entity sheet and its supporting documents, the legal entity number may be provided, unless a change in its legal status occurred in the meantime.

A Financial Identification Form conforming to the model included in the application package, certified by the bank to which the payments will be made. This bank must be located in Albania. If the Lead partner in Albania has already signed a contract with the European Commission or where the European Commission has been in charge of the payments of a contract, a copy of the previous financial identification form may be provided instead, unless a change in its bank account occurred in the meantime.

The Legal Entity Sheet and the Financial Identification Form of the Lead Partner in Albania must be presented in original.

The templates of the respective forms are also available on http://ec.europa.eu/europeaid/work/procedures/implementation/grants/index_en.htm

The hard copy of the project proposal must be submitted in 1 original and 2 copies.

The envelope must bear the following indications:

1st Call for Proposals of the “Greece-Albania IPA Cross-Border Programme” 2007-2013

Measure:…………

Project Acronym: …………….

Overall Lead Partner: ….(Name)………..

….(Address)………

NOT TO BE OPENED BEFORE THE OPENING SESSION

The Project Proposal must be submitted to the Programme’s Joint Technical Secretariat (JTS) by post, private courier service or hand-delivery, at the following address:

Joint Technical Secretariat of the “Greece - Albania IPA Cross-Border Programme” 2007-2013, 65, Georgikis Scholis Avenue, Pilea 57001, Thessaloniki, Greece

To be recognised as submitted within the fixed deadline, a proposal must be submitted until the 8/3/2011, 16:00 local time at the latest. Proposals sent after this date will not be considered as eligible. A signed and dated certificate of receipt will be handed to the deliverer.

! Attention: If the signed Project Proposal is submitted by registered mail or private courier service, only the stamp of indicating the postal date proves that the Project Proposal has been sent within the above deadline.

If the signed Project Proposal is submitted in person, only the Managing Authority’s register number is proof of timely submission.

2.4 How to fill in the Application Form

Introduction

The present chapter aims at providing the lead partners participating in the 1st call for proposals of the “Greece – Albania IPA Cross-Border Programme 2007-2013" with all information needed in order to fill in the Application Form.

The requirement of submitting an Application Form duly filled in, according to the instructions provided, is one of the formal criteria used for project evaluation. Applicants, therefore, are strongly recommended to carefully read and follow these instructions.

In addition, applicants are requested NOT to remove the protection of the Application Form or change its structure, since that could result in damaging it.

General information

When you open the “Application Form” you will be informed that it contains some macros, which you must activate, in order to obtain the properly data. Before you start working you need to save the file locally.

! Technical note: the level of security of macros should be set at “Medium”, choosing from Excel’s main menu “tools” – “macros” – “security” – “security level” – “medium”.

The Application form must be properly filled in and signed by the Overall Lead Partner. The application form consists of a cover page and seven sections describing in detail the project proposal. Information about the proposed project must be accurate and correct.

White Fields are those that must be completed by the Applicant.

Fields marked in grey are those filled in by the Managing Authority, or fields in which data are automatically transferred or calculated based on the input provided in other fields.

! While filling in the application form the applicants should take into account the limits set.

If further instructions or clarifications concerning the application form are needed, the applicant may contact the Programme’s Joint Technical Secretariat or the Managing Authority.

In case a project proposal is approved, the application form submitted constitutes part of the subsidy/grant contract. It is pointed out that compliance with the provisions of the contract is the responsibility of the Overall Lead partner as well as the other Lead Partner, while non compliance with such provisions may lead to the withdrawal of financing.

COVER PAGE

This section provides general information, such as details on the Programme in the frame of which the application form is submitted and general information identifying a proposal. Information per part and field is provided below.

Application No: Protocol number filled in by the JTS

Date of submission: Date of submission of the proposal (date of post stamp or date of direct delivery to the JTS by the Applicant) filled in by the JTS

Project title: Please insert the title of the proposed project

Project acronym: Please insert the acronym of the proposed project

SECTION A - PROJECT IDENTIFICATION

This section provides general information concerning project identification. Information per part and field is provided below.

Project title: Title of the proposed project. This field is automatically filled in with the relevant information provided in the Cover Page.

Project acronym: Acronym of the proposed project. This field is automatically filled in with the relevant information provided in the Cover Page Section.

Project duration:

Start: Please insert the date the project is ready to start (the correct date format must always be used: mm yyyy, e.g. 05  2009).  Projects should be ready to start their implementation as soon as possible after the approval decision of the Programme’s Joint Steering Committee.

End: Please insert the date the project is ready to end.  The correct format must always be used (mm  yyyy, e.g. 05   2009)

Total Months: This field is automatically calculated given the values inserted in the two previous fields.  For the recommended duration of projects, please refer to Section 2.2.3 Duration of projects of this programme manual.

Priority Axis: Please insert the title of the priority axis of the Programme in the frame of which the project is proposed (see the Programme description provided in this manual as well as the Programming Document Programme concerning the Priority Axes).  The relevant priority axis must be selected from the drop-down list.

Measure: Please specify one of the measures under the specific Priority Axis chosen, relevant with the project proposal. The measures under each Priority Axis are described in the Programming Document and must be selected from the drop-down list.

Brief Description of the Project:  Please give a very brief summary of the project’s background, objectives, partnership, main activities and expected outputs. It is strongly advised that this field is filled in after the entire Application Form has been completed. Should the project be approved, this summary will be published on the programme’s website.  Thus, it should be clear, self-explanatory and without references to other parts of the Application Form or to other documents. This field should not exceed 3000 characters.

! Due to Excel limitations, the relevant text box is split into three parts. Each part should not exceed 1000 characters. The total number of characters is automatically calculated in order to facilitate the applicants in filling this filed

Partner Information: This part provides an overview of project partnership.

Partner No: The field is automatically filled in based on the information provided in Section C of the Application Form (Partnership).

Partner Institution (Full name): The field is automatically filled in based on the information provided in Section C of the Application Form (Partnership).

Country:  The field is automatically filled in based on the information provided in Section C of the Application Form (Partnership).

NUTS III or equivalent: The field is automatically filled in based on the information provided in Section C of the Application Form (Partnership).

Legal Status: The field is automatically filled in based on the information provided in Section C of the Application Form (Partnership).

Budget per partner: This table provides an overview of partners’ financial contribution to the project and is automatically filled in based on the information provided in Section C of the Application Form (Partnership).  The fields automatically filled in are the following:

Project Partner No: The number identifying the specific partner.

Country: The country of origin of the partner.

EU Co-Financing: The EU contribution corresponding to the specific partner.

National co-financing: National co-financing corresponding to the specific partner

Total: the sum of EU contribution plus the national co-financing resulting to the total budget of the specific partner

Budget & partners per country: This part provides an overview of the number of partners and the budget per country and is automatically filled in based on the data contained in the previous table. The fields automatically filled in are the following:

Country: The country of origin of partners

Number of Partners: The number of partners from the specific country

EU Co-Financing: The EU contribution corresponding to the specific country

National co-financing: National co-financing corresponding to the specific country

Total: The sum of EU contribution plus the national co-financing resulting to the total budget corresponding to the specific country

Project title: This field is automatically filled in with the relevant information provided in the Cover Page Section

Project Budget: This table provides a summary of the project budget and is automatically filled in.  The fields contained in this table are the following:

EU Co-Financing: The EU contribution of the project

National co-financing: National co-financing of the project

Total Budget: The sum of EU contribution plus the national co-financing resulting to the total project budget

Overall Lead Partner Declaration: In this part the Overall Lead Partner confirms, by officially signing and stamping the Application Form, that:

- the project neither in whole nor in part has or will receive any other complementary EU funding (except for the funding indicated in this application form) during the whole duration of the project;

- the project is in line with the relevant EU and national legislation and policies of the countries involved;

- all partners in the partnership receiving funding from the programme are eligible bodies as defined in the Programme;

- all partners described in section C of the Application Form are committed to taking part in the project’s activities and

- all information provided in the Application Form is accurate and true to the best Knowledge of the Overall Lead Partner.

All data (Name, Title, Institution and date of signature) must be completed by the signatory (normally the Legal Representative of the Overall Lead Partner’s Institution).

SECTION B – DETAILED DESCRIPTION

This section provides a detailed description of the project idea and objectives, its structure (activities, deliverables etc), the role of partners, the management of the project etc.  This section is divided in eight sub-sections ( B1 – Project Identification, B2 – Methodological Approach, B3 – Management, B4 - Information and publicity, B5 - Maturity of the project, B6 - Sustainability of results, B7 - Cross-border cooperation & Added value and B8 - Compatibility with EU and national policies) presented below.

B1. PROJECT IDENTIFICATION

This section describes how the project idea was developed and what are its objectives and expected results.  This section contains the following fields:

Brief History of the Project: Please provide a brief description on how the project idea and partnership was developed and how the partners were involved in developing the project proposal. The maximum number of characters allowed in this field is 2000.

Background of the project (problems/issues/opportunities addressed): Please describe the reasons for which the proposed project is necessary as well as the problem(s), issue(s) and/or opportunities not currently met that the project will address. The applicants may refer to the Programme SWOT analysis and Objectives, as well as to the relevant chapters of the Manual in order to better describe the project’s background.   The maximum number of characters allowed in this field is 3000.

Objectives of the Project: Please describe the overall objective and sub-objectives of the project. The maximum number of characters allowed in this field is 2000.

Expected Outputs

Outputs are tangible and visible results or products relating to the project activities and objectives. Expected project outputs are the means to achieve the Project’s (as well as the Programme’s) objectives. These results should include the description of the output indicators that will be described and quantified in Section F – Output Indicators. Examples include: networks set up between cities, studies, databases etc.   The outputs described here should also be logically connected (be either a logical combination or be identical with) the basic project deliverables listed in Section B2 of the Application Form, in a way that it gets obvious to the reader what are the expected outputs through which the project meets its objectives.  The maximum number of characters allowed in this field is 2000.

Expected Results

Please describe the direct and immediate effects resulting from the project.  These results should include the description of the result indicators that will be described and quantified in Section F – Indicators. Additionally, the applicant may describe the innovative character of the expected results or clarify the added-value of the results compared to the achievements of previous experience (in case of a project follow-up).  The maximum number of characters allowed in this field is 2000.

Note: The project should have identifiable and measurable targets so that its progress can be monitored and evaluated in a way that ongoing consistency with the objectives of the Programme may be achieved. In case of failure in meeting the objectives, financing may be suspended; therefore targets presented should be realistic.

B.2 METHODOLOGICAL APPROACH

This section provides an analytical overview of the project’s implementation methodology (activities, their combination and sequence, responsibilities etc.). The methodology must clearly show a common and team-oriented manner of work between partners. This section contains the following fields:

Project Methodology: Please describe the approach and methodology (e.g. sequence, combination and interrelation between the activities; the logic behind the different work packages) proposed to achieve the project’s objectives and to produce the intended results. The methodology must include information about the project implementation stages and how these will contribute towards the attainment of the targets sought; identification of the tools proposed and their suitability towards the attainment of the proposed targets etc. This field should not exceed 3000 characters.

Roles - Tasks of Partners:  Please describe the division of roles and tasks among the partners (e.g. partners responsibilities for administrative and/or financial tasks, participation in the implementation of activities and deliverables, degree of involvement given the competences and strengths of each partner etc.).  This field should not exceed 2000 characters.

Work Packages / Actions/Deliverables

Please break down the proposed project into Work Packages. Having defined the objectives of the project, a more detailed plan of work packages had to be developed to map out how objectives will be achieved. Well defined objectives should make decisions on appropriate work packages relatively easy.  The work packages (WPs) identified should follow the logical phases of the implementation of the project and include management and communication activities. The number of work packages used must be relevant to the complexity of the work and objectives of the proposed project.

Work packages must be split in Actions in a way that they logically follow the project implementation sub-phases or concrete sub-sets of tasks (leading to concrete deliverables described later on). A project should be divided in at least three (3) and maximum six (6) Work packages.  Each Work Package should contain no more that five (5) Actions maximum.

Two of the 3 compulsory Work Packages are:

- “WP1 Management and Coordination” describing the sequence of Actions in order for the project to be coordinated and financially managed (including for example the necessary meetings between the partners in order to coordinate the project’s implementation, or the activities of the Lead Partner concerning the financial monitoring - reporting of the project etc.)  Management and coordination activities and the relevant costs should be duly justified. If Preparation Activities have taken place for the development of the project proposal these Activities should be the starting Action (Action 1.1) of WP1, otherwise the relevant fields of Action 1.1 should be left empty (see also Eligibility of expenditure and Preparation Costs as described in Section 2.3.2 of the Manual).

- “WP2 Information & Publicity” describing the Actions for carrying out the external communication of project efforts and outputs, dissemination of results etc.

In the following pages two (2) indicative projects are presented, being broken down into Work Packages, actions and deliverables. The first one concerns an “infrastructure project” and the second one a “soft project”

“Infrastructure” project

| WP | Action | Deliverable | Country |
| --- | --- | --- | --- |
| - Management and Coordination | 1.1 Management actions | - Progress Reports | Country 1 |
|  | 1.2 Project meetings | kick-off meeting (minutes, …) | Country 1 |
|  |  | Progress Meetings (minutes, …) | Country 1/ Country 2 |
|  |  | closeout meeting (minutes, …) | Country 2 |
| - Information and Publicity | 2.1 Information actions | 2.1.1 Web-site development | Country 1 |
|  |  | 2.1.2 2 info desks | Country 1 |
|  |  |  | Country 2 |
|  | 2.2 Printed and electronic information material | 2.2.1 50 CD-ROMs | Country 2 |
|  |  | 2.2.2 500 booklets | Country 1 |
|  |  | 2.2.3 1000 leaflets | Country 2 |
|  |  | 2.2.4 1 Newsletter | Country 2 |
|  |  | - 1 informative video production | Country 1 |
|  | 2.3 Publicity and promotion actions in the Mass Media | 2.3.1 15 entries in national Mass Media (newspapers) | Country 2 |
|  |  | 2.3.2 37 entries in national magazines |  |
|  |  | - 100 entries in the Internet |  |
| - Veterinary Diagnostic Laboratory | 3.1 Construction of a Veterinary Diagnostic Laboratory | Preliminary study | Country 1 |
|  |  | 3.1.2 1 building |  |
|  |  | - Supply of Laboratory Equipment |  |
|  | - Veterinary Laboratory Upgrading | - 1 building Renovation | Country 2 |
|  |  | - Supply of Laboratory Equipment | Country 2 |

| - Laboratory Networking | 4.1 Portal Construction | 4.1.1 Supply of equipment | Country 1 |
| --- | --- | --- | --- |
|  |  | 4.1.2 Primary Data Collection | Country 1 |
|  |  |  | Country 2 |
|  |  | - Portal development | Country 1 |
|  | - Distance learning system development | - Supply of equipment | Country 2 |
|  |  | - Application development |  |
|  |  | - Potential Users’ training |  |

“Soft” project

| WP | ACTION | DELIVERABLE | COUNTRY |
| --- | --- | --- | --- |
| 1. MANAGEMENT & COORDINATION | 1. Preparation Activities | 1.1.1. project proposal | COUNTRY 1 |
|  | 2. Project Coordination meetings | 1.2.1. kick off meeting | COUNTRY 1 |
|  |  | 1.2.2. project meetings (minutes, …) | COUNTRY 1 /COUNTRY 2 |
|  | 3. Project Management | 1.3.1 Progress Reports | COUNTRY 1 |
|  |  | 1.3.2 IT platform for the administration of the project | COUNTRY 1 |
| 2. INFORMATION AND PUBLICITY | 1. Multilingual Project communication package | 2.1.1 5.000 leaflets | COUNTRY 1 /COUNTRY 2 |
|  |  | 2.1.2 6 newsletter (1.000 copies) | COUNTRY 1 /COUNTRY 2 |
|  | 2. Open international conference | 2.2.1 Open international conference theme “….” (minutes, …) | COUNTRY 1 |
|  | 3. Workshops | 3.1.1 Workshop | COUNTRY 2 |
| 3. INVENTORY OF ARCHAEOLOGICAL SITES | 1. Documentation of archaeological monuments | 3.1.1 Catalogue of Monuments | COUNTRY 1 |
|  |  | 3.1.2 Catalogue of Monuments | COUNTRY 2 |
|  |  | 3.1.3 Archaeological map | COUNTRY 1 |
|  | 2. Information System | 3.2.1 Creation of a multilingual data base | COUNTRY 1 |
|  |  | 3.2.2 Documentation of the selected monuments in the multilingual database | COUNTRY 1/ COUNTRY 2 |
|  |  | 3.2.3 Supply of IT equipment | COUNTRY 1 |
| 4. RESTORATION AND CONSERVATION OF ARCHEOLOGICAL MONUMENTS | 1. Requirements of monuments in terms of repair, restoration and conservation. | 4.1.1 Document/ list of selected places/monuments | COUNTRY 1/COUNTRY2 |
|  | 2. Restoration and conservation studies | 4.2.1 Restoration and conservation study | COUNTRY 1/ COUNTRY 2 |

Each WP / Action contains the following fields:

Title: Please insert the title of the Work Package or Action

Start: Please insert the Start Date of each WP and Action (in case of WPs, the start date is automatically filled in, based on the Actions’ earliest start date)

End: Please insert the End Date of each Action (in case of WPs, the end date is automatically filled in, based on the Actions’ latest end date)

Cost: The Cost of Actions summing up to the costs of Work Packages are automatically filled in based on the information inserted in Section D – Budget.

Deliverables

This table describes the deliverables per action and contains the following fields:

Action No: Please select the number of Action from the relevant drop down menu (the same numbering must be used for the same Action throughout the whole Application Form).

Deliverable No: Please insert the Deliverable number (the same numbering must be used for the same Deliverable throughout the whole Application Form). Deliverable numbers must have as a prefix the Action number (e.g. 1.1) followed by the number of the specific deliverable (resulting to a three-part number)

Deliverable Title: Please insert the title describing the specific deliverable

Partner No: Please list the partners responsible for the implementation of the specific deliverable (if more than one partners will contribute to the same deliverable, each partner must be inserted in a separate line)

Partner Contribution to Deliverable: Please describe what is the contribution of the specific partner for the implementation of the deliverable.  Partners contribution to deliverables must correspond to specific costs in a justified way (the costs relating to each partner for the implementation of each deliverable (or part of it) must be indicated later in the Section Budget of the Application Form)

Location of Activities: Please provide a description of the area targeted by the project, the location of partners and activities as well as the geographical scope of the longer term effects (outputs and results). The maximum number of characters allowed is 2000.

All project deliverables should be produced and handed in English language.

B.3 MANAGEMENT

This section provides information on how the project will be administered and financially managed, in order to meet the requirements set. This section contains the following fields:

Capacity of the Overall Lead Partner and the Partners:  Please describe the Experience, Structure, Personnel, Resources, Institutional role etc. of the participating partners that indicate their relevance in the proposed project. What are the partner’s competences and experiences in the field tackled?  How will the partner contribute to the content of the cooperation and benefit from it? Have partners the capacity to directly or indirectly influence national / local / regional policies? What are the reasons for selecting the specific partner to act as the Lead Partner?

Given that this field should not exceed 4000 characters, the Applicant should attach to the Application Form documents providing additional elements to that description, for example a diagram of the Partner’s structure etc.

Project Management & Coordination: Please describe the main coordination tasks, decision making structures, procedures and/or tools as well as the way the day-to-day management of the project will be organised (including financial management). Also describe how communication between partners is organized in order to facilitate coordination and decision making procedures. This field should not exceed 2000 characters.

B.4 INFORMATION AND PUBLICITY

Information and Publicity measures- external communication of project outputs, results etc.: Please describe the communication strategy to be followed in the framework of the proposed project, pointing out ways of approaching targeted groups and disseminating its results. Describe the project publicity plan and explain how it complies with the rules of publicity of the Programme. This field should not exceed 2000 characters.

B.5 MATURITY OF THE PROJECT

Preparatory activities, administrative activities undertaken etc.: Please describe the progress of any preparatory actions necessary in order to start the project implementation,  the compatibility of the project with the existing legal framework, the adequacy in progress of studies and licensing needed, the progress of administrative operations etc. This field should not exceed 2000 characters.

B.6 SUSTAINABILITY OF RESULTS

Sustainability of results and follow-up actions: Please describe how the durability of the project’s achievements will be ensured.  How, when and by whom will the outputs be used and how will they be maintained after the end of the project? What are the actions required to make the project functional upon completion (time required, administrative structure and staffing).  How will the results/impacts of the project be sustained? This field should not exceed 2000 characters.

B.7  CROSS-BORDER COOPERATION & ADDED VALUE

Intensity of Cross-Border Cooperation: Please indicate in which ways shall the partners co-operate (min one of the following four: joint development, joint implementation, joint staffing, joint financing) providing a justification of the added value that will be accomplished through each particular way. These ways of cooperation are described in more detail in the section 2.3.1 of this manual.

This field should not exceed 2000 characters.

Capitalization of previous Cross-Border Experience (if applicable): Describe, if applicable, if and how the project is linked – in terms of its synergy, complementarity, integration or capitalisation of experience – with other implemented European cooperation projects. Describe if the project aims at analysing results and/or identifying the previous INTERREG knowledge, at transferring results achieved by working through the wealth of existing experience and identifying links to EU programmes and initiatives, at sharing and disseminating this knowledge to target groups and stakeholders etc.

B.8  COMPATIBILITY WITH EU AND NATIONAL POLICIES

Consistency of the project with EU horizontal policies: Please state (by the appropriate selection) if the theme tackled by the proposed project will address directly or indirectly each of the EU horizontal policies (Equal opportunities, Sustainable Development, Environment, Open Market)

Other EU / National Policies (please specify): Please describe how the proposed project is in line with and/or complements actions undertaken in the framework of interventions carried out at a national and/or regional level.

SECTION C - PARTNERSHIP

This section provides contact and other useful details concerning the partners participating in the project implementation, starting with the Overall Lead Partner. The total number of partners must not exceed 5.

Partner Details

Name of institution in English: Please provide the official translation in English of the name of the partner’s institution.

Name of institution in original language: Please provide the name of the partner’s institution in the original language.

Distinctive Title: Please specify the distinctive title of the partner’s institution.

Legal Status: Please specify the legal status of the partner in accordance with national legislation, by selecting a value from the drop-down list.

Date of Registration: Please indicate the date of registration of the partner’s institution (or participating branch)

Place of Registration: Please indicate the place of registration of the partner’s institution (or participating branch)

Legal Representative: Please provide the name of the legal representative of the partner. The legal representative is a natural person authorised to represent and bind the institution. In the case of the Lead Partner, the legal representative of the institution must sign the Application Form.

Position of the legal representative in the organisation: Please specify the position of the legal representative in the organisation.

Contact Person for the project: Please specify the name of the person that is nominated as the contact person for the project.

Project Manager: Applicable only to the Lead Partners. Please provide the details of the person nominated as the Project Manager. The person responsible for the project should be a staff member of the lead partner who has an overall picture of the project and who coordinates the preparation of the application form on behalf of the partnership.

Financial Manager: Applicable only to the Lead Partners. Please provide the name of the person nominated as the Project Financial Manager that will be responsible for monitoring all financial aspects related to the project’s implementation.

The same person can be designated as both Project Manager and Financial Manager. If the person designated as Financial Manager is permanent staff of the partner, the designation can be done at the stage of presenting the Application Form. If the Person designated as Financial Manager will be external, the word “external” should be filled in at the stage of presenting the Application Form. For approved projects, the actual name of the person that will result from the public call procedure will be nominated when available.

Address: Please provide the full postal address of the Partner’s institution.

Partner’s country: (fill in when partner’s country of origin is different than Greece or Albania): Please provide the country of origin of the specific partner. In this case, the next “Country” field shall be filled in based on the location of the activities that will take place, during project’s implementation.

Country: Please provide the country of origin of the specific partner, by selecting a value from the drop-down list.

NUTS III code: Please provide the NUTS III code of the area (or equivalent) where the partner is located, by selecting a value from the drop-down list.

Telephone: Please provide the telephone number of the Contact Person of the Project.

e-mail: Please specify the e-mail of the Contact Person of the Project.

Fax: Please specify the fax number of the Contact Person of the Project.

website: Please provide the website address of the partner’s institution.

VAT status (eligible or not): Indicate Yes or No in the respective field to clarify whether VAT is eligible or not.

Tax Office: Please specify the Name of the Partner’s Tax Office

Tax Number: Please specify the Tax number or the Social Security Number of the Partner’s Institution.

Budget of Partner

Total Budget: This field is automatically filled in and concerns the total budget corresponding to the specific partner.

EU Co-financing: This field is automatically filled in and concerns the EU contribution corresponding to the specific partner.

National Contribution: This field is automatically filled in and concerns the national contribution corresponding to the specific partner.

Bank Details of Partner

Bank details should be filled in after the approval of the project proposal.

Bank Name: Please provide the name of the Bank Institution where the specific partner holds an account related to the project payments.

Address: Please provide the address of the Bank Institution.

Postal Code: Please provide the postal code of the Bank Institution.

Town: Please provide the name of the town where the Bank Institution is located.

Country: Please specify the country where the Bank Institution is located.

IBAN: Please specify the International Bank Account Number.

SWIFT code: Please specify the SWIFT Code.

Holder of the account: Please specify the original name of the account holder.

SECTION D - BUDGET

This section provides information on the project budget and its analysis.  You should keep in mind that all fields marked in grey are automatically filled in based on the information provided in other parts of the Application Form.

Project Budget

This table summarizes the project budget information and is automatically filled in. It contains the following fields:

EU Co-financing: The EU contribution corresponding to the specific project.

National co-financing: The national contribution corresponding to the specific project. National co-financing of  partners in Albania must be covered with own funds.

Total Budget: the sum of EU contribution plus the national co-financing resulting to the total budget corresponding to the specific project.

Total Costs per Action / Budget Line

This table summarizes the total project costs per action and budget line and is automatically filled in based on the information provided in the following tables that present the costs per partner, action and budget line (these will be further analyzed).

Costs per Country / Action / Budget Line

This table summarizes the project costs per country, action and budget line and is automatically filled in based on the information provided in the following tables that present the costs per partner, action and budget line (see next paragraph).

Costs per Partner / Action / Budget Line – Partner X

The following tables present the costs per action and budget line for each partner participating in the project, starting with the Overall Lead Partner.

For each Action of the project where the specific partner participates, must be presented how the total costs corresponding to that specific Partner for the implementation of that action are split among the different budget line categories.  The Totals per Work Package, Action and Budget line are automatically filled in and marked in grey.

Costs per Deliverable and Partner

This is the same table presented in Section B.2 – Methodological Approach of the Application Form that describes the deliverables per project action and partner, with an additional field describing the cost per deliverable and partner.  Only the field costs should be filled in, as the first five fields are automatically filled in based on the information inserted in Section B.2.  For each deliverable and partner the field costs must be filled in with the cost corresponding to that partner for the implementation of the specific deliverable.

NOTE: The Applicant must attach to the Application Form as Annexes the Justification of budget costs for the proposed activities (providing concrete examples of the way Action/Deliverable costs have been calculated). This justification could include, for example, calculations based on man-months of effort for the tasks described, specific offers for supplies etc.

SECTION E – TIMETABLE

This section provides information on the actions’ implementation timetable as well as the provisional allocation of the project budget per action and reporting period.

Timetable

The duration of each action and Work Package, in months, is filled in automatically, based on the information provided in fields “Start” and “End”, in the Section B2. “Work packages – Actions”.  The project should be concluded within 18 months from the signing of the subsidy contract.

Budget per reporting period

Please specify the provisional allocation of the budget in the 3-month reporting periods covering the project’s duration. In each field representing a reporting period of the Year X specify the budget in euros that corresponds to the part of the budget of the specific Action / WP that will be spent during this period.  The Totals per Action and per Reporting Period will be filled in automatically.

SECTION F – INDICATORS

This section provides information on the outputs and results which are expected to be achieved by the proposed project.

Priority Axis: The priority axis, under which the specific project is proposed, is automatically filled in based on the relevant information provided at the Project Identification Section (Section A) of the Application Form.

Measure: The measure, under which the specific project is proposed, is automatically filled in based on the relevant information provided at the Project Identification Section (Section A) of the Application Form.

Output Indicators

Outputs are tangible and visible results or products relating to project activities. Outputs are quantified through the use of indicators. Expected project outputs will contribute to the aims of the specific Priority and / or Sub-theme. Output indicators are measured in physical or monetary units.

Indicators: The output indicators defined in the Programme for the specific Priority Axis and the specific objective are filled in automatically, based on the tables below:

| Output Indicators Priority Axis 1: “Enhancement of cross-border economic development |  |  |  |
| --- | --- | --- | --- |
| Measures | Indicator | Measurement |  |
| Measure 1.1 Promote entrepreneurship | Number of Projects contributing to the promotion of entrepreneurship | Number |  |
| Measure 1.2 Promote sustainable tourism | Number of Projects contributing to the promotion of sustainable tourism development | Number |  |
| Measure 1.3 Enable people to people actions | Number of Projects contributing to “people to people” actions | Number |  |
| Measure 1.4 Facilitate border accessibility through small scale infrastructure | Number of Projects contributing to border accessibility | Number |  |

| Output Indicators Priority Axis 2: “Promotion and development of the environment and natural and cultural resources” |  |  |  |
| --- | --- | --- | --- |
| Measures | Indicator | Measurement |  |
| Measure 2.1 Promote and protect the environmental resources of the area | Number of Projects contributing to the protection of the environmental resources of the area | Number |  |
| Measure 2.2 Promote and protect the natural and cultural heritage of the area | Number of Projects contributing to the protection and promotion of the natural and cultural heritage | Number |  |

Measurement: Output indicators are measured in physical or monetary units.  The measurement units of the predefined output indicators are filled in automatically, based on the information provided above.

Target: Please specify the targeted value of each output indicator.

Result Indicators

Results refer to the immediate impacts derived from the project implementation. Project results must refer to the objectives of the specific Priority Axis or Sub-theme. Results are quantified through the use of indicators. At least the indicators set out in the Programme must be used. If deemed necessary for better presentation of the results of the proposed project, additional indicators, besides those described in the Programme, may be used.

Indicators: The result indicators defined in the Programme for the specific Priority Axis and the specific objective are filled in automatically, based on the tables below:

| Result Indicators Priority Axis 1: “Enhancement of cross-border economic development |  |  |  |
| --- | --- | --- | --- |
| Measures | Indicator | Measurement |  |
| Measure 1.1 Promote entrepreneurship | Contributions to the economic development of the eligible border area | Reporting of contributions |  |
| Measure 1.2 Promote sustainable tourism | Contributions to the tourism development of the eligible border area | Reporting of contributions |  |
| Measure 1.3 Enable people to people actions | Contributions to the closer relations of the people in the eligible border area | Reporting of contributions |  |
| Measure 1.4 Facilitate border accessibility through small scale infrastructure | Contributions to the border accessibility | Reporting of contributions |  |
| Priority Axis 2: “Promotion and development of the environment and natural and cultural resources” |  |  |  |
| Measures | Indicator | Measurement |  |
| Measure 2.1 Promote and protect the environmental resources of the area | Contributions to the protections and promotion of the environment | Reporting of contributions |  |
| Measure 2.2 Promote and protect the natural and cultural heritage of the area | Contributions to the protection and promotion of the natural and cultural heritage | Reporting of contributions |  |

Measurement: The measurement units of the predefined result indicators are filled in automatically, based on the information above.

Target: Please specify the targeted value of each result indicator.

SECTION G – CHECKLIST FOR SUBMISSION

This section provides a checklist of requirements that have to be fulfilled before officially submitting the project proposal. Please make sure that you have fulfilled all of the requirements listed in that section by clicking on each checkbox, before submitting the documents.

## 2. 5 Evaluation Procedure

After submission, each application will be subject to a two-phase selection procedure, carried out by the Joint Technical Secretariat, based on the selection criteria described below. In order to carry out the evaluation procedure, the JTS may be assisted by external experts. The procedure, as well as the criteria for the selection of these experts will be mutually agreed by the participating and will be approved by the Joint Monitoring Committee.

1st phase: Projects will be checked against their administrative compliance and eligibility criteria, in order to ensure that they fulfill the administrative and technical requirements of the Programme. This is an on-off procedure. Projects which fail to fulfill the technical requirements of the Programme will be excluded from the 2nd phase and the Lead Partner will be informed in writing.

2nd phase: Only projects that demonstrate administrative compliance and satisfy the eligibility criteria will be subject to quality assessment. The quality assessment is based on a scoring system and results in a ranked list of all the applications that have passed the 1st phase. It will be carried out by the JTS. The JTS may be assisted by external experts during the project evaluation.

The JTS and external experts nominated by the program management bodies will examine three different sets of criteria, in order to make a decision on the project’s approval. Namely:

1st phase analysis

Projects will be checked against two sets of criteria, in order to ensure that they fulfill the administrative and technical requirements of the Programme.

- Administrative compliance: It confirms that a proposal has been submitted within the deadline set; the Application Form has the official form specified by the Managing Authority, is complete and meets all the requirements set in the respective Call;

- Eligibility criteria: These criteria examine whether the proposal fulfils the minimum requirements for being eligible for funding by the Programme. These requirements are, for instance, the structure of the cross-border partnership, the general compatibility with the Programme objectives and principles, the grant requested, etc. Proposals which do not fulfill the eligibility criteria are identified and additional information is requested from the applicant or they are rejected, depending on the particular case;

2nd phase

Quality of the project: The quality assessment will only apply to projects that have successfully gone through the 1st phase.  During this phase, proposals are evaluated using core selection criteria. These entail evaluating the nature of the proposed operation, its relevance with and contribution to the Operational Programme’s overall objectives, its timeframe, viability and results in the eligible territory, the quality of the cross-border partnership as well as the monitoring, management and evaluation methodology proposed.

The Core selection criteria are divided into:

- Content-related criteria (relevance of the proposal, quality of results/ sustainability, innovation) and

- Implementation-related criteria (quality of the partnership, coherence of the proposal and quality of approach, budget and finance).

The different sets of criteria are presented in Annex I. Project Selection Criteria.

The Joint Technical Secretariat carries out the evaluation of proposals, based on these selection criteria, approved by the Joint Monitoring Committee. The Managing Authority ensures that the evaluation procedure was carried out in accordance with the requirements of the call for proposals and the approved selection criteria.

After the MA has accepted the evaluation, submits to the EU Delegation in Albania the ranking list of evaluated project proposals for comments and coordination, providing reasonable time for reaction.

Then, the MA submits to the Joint Steering Committee:

1) the application forms of the submitted project proposals,

2) a ranking list of all evaluated project proposals and

3) all evaluation forms.

The projects are ranked according to the results obtained and applications are divided into three categories (based on the budget available and the results of evaluation):

- Applications proposed to be accepted;

- Applications proposed to be rejected and

- Applications proposed to be further discussed at the Joint Steering Committee (acceptable under conditions).

To be considered for financing by the Programme, a project must:

- obtain a rating equal or greater than the minimum score entitling a project to be financed (60 points);

- obtain at least 50% of the maximum score in each of the two afore-mentioned categories of the “Core selection criteria” (Implementation-related criteria, Content-related criteria);

In case that more than one proposals receive the same score and qualify for the last project to be financed – within the specified allocation of funds of the Call for Proposals - preference shall be given to the project with the highest aggregate score in the ‘Quality of the Partnership’ criterion.

The Joint Steering Committee selects the operations to be funded. If a proposal is accepted under conditions, the Managing Authority will have to check that these conditions are met before subsidy contracts are signed with the competent Authorities.

# 3. Project Implementation Manual

## 3.1 Contracting of a Project Proposal

On the basis of the Joint Monitoring Committee’s decision (selected project proposals), the Managing Authority as well as the European Union Delegation to Albania shall sign the relevant contracts with the Lead Partners as well as with the Overall Lead Partner of the projects, as described earlier.

The formal endorsement by the EUD in Albania of the Final List and the signing and submission of the Partnership Agreement to the JTS is a prerequisite for the signing of the Contracts.

In case of approval of project’s under conditions, the revised Application Form is also a prerequisite for the signing of the relevant Contracts.

## 3.2 Reporting procedures

The Overall Lead Partner is the Lead beneficiary in accordance with art 96 of Commission Regulation 718/2007 for the project. It is responsible for the submission to the Joint Technical Secretariat (JTS) of progress reports on the entire project implementation in accordance with the timetable referred to, in the approved Application Form and the Programme Manual as in force.

Prior to filling in a progress report, the Overall Lead Partner will collect the expenditure made by all project partners including itself.  Expenditure of the partners in Greece must be accompanied by the relevant verifications signed by the competent controllers. The verified expenditure of these partners must be attached to the relevant progress reports. The Overall Lead Partner will use the official forms (Progress Reports), which are provided by the MA/JTS.

Should the Project Partners delay in submitting to the Overall Lead Partner their activity and financial reports, the Overall Lead Partner will still abide by the deadlines for submission, updating and sending to the Joint Technical Secretariat the reports when the missing information becomes available. However, should the Project Partners delay in submitting to the Overall Lead Partner their table of verified expenditure, the Overall Lead Partner will add the missing information to the statement of the next reporting period.

All reports must be submitted in English, which is the official language of the Programme.

The Joint Technical Secretariat receives and processes progress reports, together with the necessary supporting documents. The Managing Authority has the final responsibility of providing its’ consent to the competent Authorities, in order to initiate the payments to the Lead Partner in Greece (see also section 3.3).

The Joint Technical Secretariat, Managing Authority, Certifying Authority, the National Coordinators, and the European Commission may at any time ask for supplementary information concerning payments or the project itself.

| Reporting Periods | Deadlines for the submission of progress reports |
| --- | --- |
| January - March | 20th of April of the respective year |
| April - June | 20th of July of the respective year |
| July - September | 20th of October of the respective year |
| October – December | 20th of January of the respective year |
| Final Report | Together with the last progress report |

Considering that payments of European Union’s contribution to the Lead partners in Greece are made by the European Commission in accordance with the European Union’s provisions concerning the budget commitments of the Structural Funds, the Overall Lead Partner will submit a progress report to the JTS every three months in accordance with the following schedule:

As indicated in the above table, the deadline for the submission of the Progress Report is 20 days from the end of the Reporting Period. Partners in Greece should send the expenditure of each month to the designated controller according to the reporting period.

Interim progress reports may be requested by the Managing Authority of the Programme for financial management reasons at any stage.

Partners from Albania should also refer to the reporting requirements and obligations for supporting documentation described in Grant Contract between the EU Delegation and the Lead partner in Albania.

How to fill in the Progress Report

1. General Project Information

Priority Axis: Please insert the title of the priority axis of the Programme in the frame of which the project has been approved. The priority must be selected from the drop-down list.

Sub – theme: Please specify one of the types of actions under the specific Priority Axis chosen, relevant with the project, as described in the approved Application Form

Project title: Title of the project.

Project acronym: Acronym of the project.

Project code number: Please insert the Project Code Number, as declared in the Subsidy Contract.

Overall Lead Partner: Please insert the full name of the institution in English, as stated in the approved Application Form.

Country of Overall Lead Partner: Please insert the country of origin of the partner, as stated in the approved Application Form.

Reference number of the Overall Contract  - LP1 (OLP): Please insert the reference number of the contract signed between the MA and the OLP

Reference number of the Subsidy Contract A  - LP1 (OLP): Please insert the reference number of the subsidy Contract A signed between the competent Authority (MA or Delegation of the European Union) and the LP1.

LP2: Please insert the full name of the institution in English, as stated in the approved Application Form.

Country of LP2: Please insert the country of origin of the partner, as stated in the approved Application Form.

Reference number of the Subsidy Contract B  - LP2: Please insert the reference number of the contract signed between the competent Authority (MA or Delegation of the European Union) and the LP2.

Legal Representative: Please provide the name of the legal representative of the partner, as stated in the approved Application Form.

Position of the legal representative in the organisation: Please specify the position of the legal representative in the organisation.

Project Manager: Applicable only to the Lead Partner. Please provide the details of the person nominated as the Project Manager. The person responsible for the project should be a staff member of the Lead Partner who has an overall picture of the project implementation.

Financial Manager: Applicable only to the Lead Partners. Please provide the name of the person nominated as the Project Financial Manager and will be responsible for monitoring all financial aspects related to the project’s implementation by the partners from its country.

The same person can be designated as both Project Manager and Financial Manager. If the person designated as Project / Financial Manager is permanent staff of the partner, the designation can be done at the stage of presenting the Application Form. If the Person designated as Project / Financial Manager will be external, the word “external” should be filled in at the stage of presenting the Application Form. For approved projects, the actual name of the person that will result from the public call procedure will be nominated when available.

Reporting Period:

Start: Please insert the date that the reporting period starts (the correct date format must be used: mm-yyyy, eg 05-2009).

End: Please insert the date that the reporting period ends (the correct format must be used (mm-yyyy, e.g. 05-2009) according to the approved Application Form.

Duration: This field is automatically calculated given the values inserted in the two previous fields.

Progress Report Number : Please insert the progress report number indicating the number 1 for the 1st Progress Report, the number 2 for the 2nd Progress Report.

Timeframe of the project:

Start: Please insert the date that the project starts (the correct date format must be used: mm-yyyy, eg 05-2009) according to the approved Application Form.

End: Please insert the date that the project ends (the correct format must be used (mm-yyyy, eg 05-2009) according to the approved Application Form.

Duration: This field is automatically calculated given the values inserted in the two previous fields.

PROGRESS REPORT SUMMARY

2.1   Summary of the project's achievements in this reporting period (not more than 300 words): Please describe the main achievements of the project during this reporting period with reference to the relative work packages, actions, outputs and results. Please describe the involvement of partners in the implementation of the project during the current reporting period. Was the involvement of partners according to the plans or did you encounter any problem?

2.2   Summary of the project's achievements so far (not more than 300 words): Please describe the main achievements of the project until today with reference to the relative work packages, actions, outputs and results. This section should include the experience gained and the added-value of cooperation as well as any problems encountered and the ways they were dealt with.

2.3   Changes in the Implementation: Please refer to heading 3.4 below for guidelines related to changes in the implementation.

3.    OUTPUTS ACHIEVED WITHIN THE REPORTING PERIOD

Indicators: Please fill in the Indicators as stated in the approved Application Form

Unit of Measurement: Please fill in the Units of Measurements as stated in the approved Application Form.

Target Value: Please specify the targeted value of each output indicator as stated in the approved Application Form.

Achieved Value (current period): Please fill in the value achieved during the particular reporting period.

Total cumulative value: Please fill in the total value achieved from the beginning of the project until the end of the current reporting period.

4.    RESULTS ACHIEVED WITHIN THE REPORTING PERIOD

Indicators: Please fill in the Indicators as stated in the approved Application Form

Unit of Measurement: Please fill in the Units of Measurements as stated in the approved Application Form.

Target Value: Please specify the targeted value of each result indicator as stated in the approved Application Form.

Achieved Value (current period): Please fill in the value achieved during the particular reporting period.

Total cumulative value: Please fill in the total value achieved from the beginning of the project until the end of the current reporting period.

5.    FINANCIAL INFORMATION AND TIMEFRAME

  - Implementation of actions: Please state the deliverables implemented within the specific reporting period using the table provided. Actions that start in one and finish in the next Reporting Period should be declared in both reports.

Action No: State

Action No: Please insert the number of Action as stated in the approved Application Form.

Deliverable No: Please insert the Deliverable number as stated in the approved Application Form.

Deliverable Description: Please insert the title (description) of the specific deliverable as stated in the approved Application Form.

Start: Please insert the date that the action starts (the correct date format must be used: mm-yyyy, eg 05-2009) according to the approved Application Form.

End: Please insert the date that the action ends (the correct format must be used (mm-yyyy, eg 05-2009) according to the approved Application Form.

Partner No: Please list the partners responsible for the implementation of the specific deliverable as stated in the approved Application Form.

Approved Budget: Please fill in the budget of the respective action as stated in the approved Application Form.

Contracted Budget: Please indicate contracted expenditures (both outsourcing and in-house implementation are included).

Payments during this reporting period: Please fill in the total amount of expenditures concerning this specific action paid out in this particular reporting period.

Verified expenditures during this reporting period: Please fill in the total amount of expenditures concerning this specific action that have been verified in this particular reporting period regardless of the period in which they have been incurred or been paid for.

5.2  Project costs per partner, working package, actions and categories of eligible expenditure

Please indicate only expenditures that have been VERIFIED within the specific Reporting Period for each Project Partner regardless of when they have been incurred or been paid for.

The Working Packages and Actions rows will be filled in, for each of the participating Partners.

Partner: Indicate for each Partner verified costs per Work Package, Action and Category of Expenditure.

Work Package: Please fill in the Work Packages involving the specific Partner, as stated in the approved Application Form.

Actions: Please fill in the Actions involving the specific Partner, as stated in the approved Application Form.

Staff Costs: Please fill in the Verified Costs under the particular category of expenditure for the specific partner and specific Work Package/Action.

Overheads: Please fill in the Verified Costs under the particular category of expenditure for the specific partner and specific Work Package/Action.

Travel and Accommodation: Please fill in the Verified Costs under the particular category of expenditure for the specific partner and specific Work Package/Action.

External Expertise and Services: Please fill in the Verified Costs under the particular category of expenditure for the specific partner and specific Work Package/Action.

Equipment: Please fill in the Verified Costs under the particular category of expenditure for the specific partner and specific Work Package/Action.

Investments/Infrastructure: Please fill in the Verified Costs under the particular category of expenditure for the specific partner and specific Work Package/Action.

Verified expenditure during this reporting period: Please fill in the amount of expenditures concerning each specific partner and work package/action action that have been verified in this particular reporting period.

Total Verified expenditure including this reporting period: Please fill in the amount of total expenditures concerning each specific partner and work package/action action that have been verified including this reporting period.

  - Verified and Paid Out Costs per Partner

Partner No: Please indicate the Partner number as stated in the approved Application Form.

Partner Institution (Full Name): Please indicate the Partner Institution Full name in English as stated in the approved Application Form.

Country: Please insert the country of origin of the partner as stated in the approved Application Form.

Payments during this Reporting Period : Please indicate expenditures paid out during this reporting period for each specific partner and Work Package/Action

Total Payments including this reporting period : Please indicate accumulative expenditures paid out including this reporting period for each specific partner and Working Package/Action

Verified expenditure during this reporting period: Please indicate expenditures that have been verified during this reporting period for each specific partner and Work Package/Action

Total verified expenditure including this reporting period: Please indicate total accumulative expenditures that have been verified including this reporting period for each specific partner and Work Package/Action

Total approved budget: Please fill in the total approved budget per partner as stated in the approved application form.

  - Project Funding Per Partner and Source : To be filled in using the information provided in table 5.2.

5.5 Project Funding per year and Partner

Please indicate all VERIFIED costs from the beginning of the project until today.

6. Deviations from the original plans : Please explain and justify any financial deviations that occurred in this reporting period such as any over- or underspending compared with the original budget by budget line.

7. Publicity: Please state the measures of publicity and / or measures of diffusion of information that have been carried out according to the submitted application form, as well as any additional ones.

Have EU requirements on information and publicity measures acknowledging EU assistance been complied with?

YES:If yes, give details.

NO: If no, please provide an explanation.

8.  		PROGRESS INDICES

Please calculate and fill in the progress of the project in % of implementation from the beginning of the project until the end of the current Reporting Period.

- List of annexes

- Annex 1: Please attach all first level control verifications of all partners reporting expenditure in this progress report

- Annex 2: Please attach the First Level Controller Accreditation Certificate (for all partners with a decentralised first level control system)

- Annex 3: Please provide any other general information on the project's implementation (Update of contact details: Have the contact details of the Lead Partner/project manager/financial manager/project partners/first level controllers changed?)

## 9. Payments / cash flows

Payment requests for project expenditure actually made will derive from the relevant reporting period progress reports. Payment of the eligible preparation costs, as specified in chapter 2.2.2 of this manual, will be included in the first progress report. Payments are made subject to the approval of progress reports by the Managing Authority.

Cash flows in Greece

Following the approval of the progress reports, the Certifying Authority will transfer the EU contribution to an interest-free bank account indicated by the Lead Partner located in Greece in the application form. Payments from the Certifying Authority to the respective Lead Partner will be made in euro.

The LP shall further transfer the respective EU contribution to the PPs in Greece within one month of its receipt.

The amounts will be paid according to the flow of funds from the European Commission.

Cash flows in Albania

The European Union’s Contribution for LPs in Albania is going to be paid by the EU according to Annex 2 – Article 15 from the General Conditions applicable to European Union, Financed Grant Contract for External Actions (Grant Contract to be signed between the DEU and respective LPs).

The LP shall further transfer the respective European Union’s contribution to the PPs from Albania within two weeks of its receipt.

The amounts will be paid according to the flow of funds from the European Commission.

National Contribution

The State co-financing plus the Own Contribution equals the National Contribution for each country.

For Partners in Greece the national contribution equals State Contribution (25%) and will be granted through the Public Investments Programme (Partners in Greece will not provide own Contribution to the project’s budget).

For Partners from Albania, the 15% contribution must be financed from own resources, or from sources other than the European Union budget or the European Development Fund.

## 3.4 Project modifications

Introduction

During the lifetime of a project internal or external causes may bring minor of major changes. These changes are usually evident in the case of innovative actions. Nevertheless, in order to secure success during the implementation phase, partners need to follow a structured form with a precise time table and well defined actions and results. The Application Form describes each project in detail providing specific information such as timetables, financial information, budget forecasts etc. The Application Form together with the Contracts signed and the Partnership Agreement provide the basis for project implementation. The Programme’s Joint Steering Committee approves projects based on the information provided in the Project Proposal comprising the Application Form and annexed documents. Therefore, Lead Partners and Project Partners have a degree of freedom to develop the projects but should follow the terms of the Contracts signed. Changes occurring during the lifetime of a project in general should not affect this basis. Nonetheless, there may be cases for an inevitable exception. The main object of this chapter is to describe the different categories of related project changes. It is important to note that approval of project changes should not be considered an automatic procedure.

Definition of categories of projects changes

Three main categories of project changes can be defined, these are:

a) project modifications;

b) financial flexibility rule (20% rule);

c) administrative information.

- Project modifications are changes to the project plan which need special approval by the Managing Authority and the Delegation of the EU as well as of the Joint Steering Committee based on the specific case,

- Administrative Information includes changes of contact details and other data of minor significance.

a. Project Modifications

The Overall Lead Partner must address the JTS (in accordance with the requirements set out in article Article 7 of the relevant contract) any requests for modification of the project. The request for modification must be duly justified.

Modifications approved directly by the Managing Authority with the endorsement of the Delegation of the European Union:

- Reallocation between the respective budget categories for amounts up to 20% of the total budget of the project (except for yearly budget reallocations),

- Extension of the date set for closing project implementation activities, if not affecting the achievement of the target set by the n+3,

- Reallocation of resources between partners from the same participating country, at the same EU rate of contribution, which may result in a change equal to or less than 10% of the project budget (EU + National Funding).

Reallocation of funds between partners may be accepted only if it does not involve an increase in the EU contribution of the project.

Procedure for the approval of the above mentioned cases of project modifications: After the approval of the modification proposal by the Project Management Team, the Overall Lead Partner submits a request to the Joint Technical Secretariat, which forwards it according to its internal rules of procedures to the Managing Authority of the Programme. The Managing Authority decides upon the approval of the request, taking under consideration information provided by the Joint Technical Secretariat in consultation with the EUD. Any relevant claim must be sent to the JTS no later than 40 days prior to the date on which the proposed modification is requested to become effective.

Modifications approved by the Joint Steering Committee:

- Reallocation between the respective budget categories for amounts greater than 20% of the total budget (except for yearly budget reallocations). Budget reallocation between Budget Lines over 20% of the total budget may occur only if the requested change does not alter the minimum requirements, the planned action, outputs and results and does not endanger the general project principle of co-operation. In addition to the above it is crucial for a project to keep constant those categories that are of crucial importance for the project implementation and the partners’ cooperation.

- Reallocation of resources between partners from the same participating country, at the same EU rate of contribution, which may result in a change greater than 10% of the project budget (EU + National Funding).

Reallocation of funds between partners may be accepted only if it does not involve an increase in the EU contribution of the project.

- Changes to the nature of the project and in particular to the objectives and the expected results. In principle it is not allowed to change the content of the project, especially the objectives and the expected results. However, in some cases modification of the approved project structure might be necessary. These changes must be well justified and described as soon as they become evident.

- Modification to the composition of the partnership.

- Budget modifications decided by the Joint Steering Committee on the basis of sound financial management of the Programme.

Procedure for the approval of the above mentioned cases of project modifications: After the approval of the modification proposal by the Project Management Team, the Overall Lead Partner submits a request to the Joint Technical Secretariat that forwards it according to its internal rules of procedures to the Managing Authority of the Programme. The Managing Authority taking under consideration information provided by the Joint Technical Secretariat, presents its proposal to the Joint Steering Committee that decided the approval of the request.

Any relevant claim must be sent to the JTS no later than 60 days prior to the date on which the proposed modification is requested to become effective.

b. Administrative Information

For a change of postal address/telephone/email address a simple written notification to JTS  is required. The same applies for changing a bank account. However, the MA reserves the right to object to the choice of the type of account opened by the beneficiary. Changing the bank account must be stated in progress reports.

Budget reduction

In case that one year after the singing of the subsidy contract and provided that the total verified expenditure reported in progress reports, as regards the previous year, is less than 20% of the total budget for the project, the Managing Authority reserves the right to consider the possibility of reducing the approved budget of the project. In this case immediate communication should be made to the Overall Lead partner and project partners.

In case that the EU annual contribution (as stated in the Operational Programme Document) is automatically de-committed by the European Commission, in accordance with Article 166 of Reg. (EC, Euratom) No 1605/2002, the Managing Authority reserves the right to consider the possibility of reducing the approved budget of the project with respect to expenditure not carried out in accordance with the stipulated timetable.

In both cases the Joint Monitoring Committee, after the proposal of the Managing Authority, may decide to reduce the budget of the project. If the reduction of the project budget is decided, the subsidy contract and respective annexes will be modified accordingly.

## 3.5 FIRST LEVEL CONTROL

In Greece, there is a centralized system of expenditure verification as described in the Ministerial Decree 9771/DIOE/470/20-2-2009.

In Albania, all expenditure will be verified by external auditors before the submission to EU Delegation to Albania. The cost of verification shall be eligible for co-financing by the project budget.

# ANNEXES

## I. PROJECT SELECTION CRITERIA

## II. PARTNERSHIP AGREEMENT

## III. CONTRACTS

## IV. PROGRESS REPORT

Groups/entities that will be directly positively affected by the project at the Project Purpose level,

Are those who will benefit from the project in the long term at the level of the society or sector at large.

Bodies governed by public law as defined in Article 1(9) of Directive 2004/18/EC of the European Parliament and of the Council of 31 March 2004 on the coordination of procedures for the award of public works contracts, public supply contracts and public service contracts (http://eur-lex.europa.eu/LexUriServ/LexUriServ.do?uri=OJ:L:2004:134:0114:0240:EN:PDF) and in compliance with the national legislation of each participating country.

Profit is the making of gain in business activities for the benefit of the owners of the business (paying out dividends).