# SPECIAL CONDITIONS

# CONTENTS

These conditions amplify and supplement, if necessary, the General Conditions governing the Contract. Unless the Special Conditions provide otherwise, those General Conditions remain fully applicable. The numbering of the Articles of the Special Conditions is not consecutive but follows the numbering of the Articles of the General Conditions. In exceptional cases, and with the authorisation of the appropriate Commission departments, other clauses may be added to cover specific situations.

Article 2	Language of the Contract

2.1	The language used shall be English.

Article 4	Communications

4.1	Any written communication relating to this Contract between the Contracting Authority and/or the Project Manager, on the one hand, and the Contractor on the other must state the Contract title and identification number, and must be sent by post, fax, e-mail or by hand.

National Authorizing Officer for EDF

Attention of: Mr. R. Asiedu Danquah - Head, ACP-EU Unit,

Ministry of Finance and Economic Planning, Room 341

P.O. Box MB 40

Accra- Ghana

Email: rdanquah@mofep.gov.gh / ckipo@mofep.gov.gh

[Contractor]

Article 6	Subcontracting

6.3	When selecting subcontractors the Contractor must give preference to natural persons or companies from ACP States capable of implementing the tasks required on similar terms.

Article 8	Assistance with local regulations

The Office of the National Authorising Officer for EDF at the Ministry of Finance and Economic Planning will provide the necessary assistance with local regulations and their implementing authorities.

Article 10	Origin

## 10.1	All goods purchased must originate in a Member State of the European Union or a country covered by the 10th EDF programme. For these purposes, ‘origin’ means the place where the goods are mined, grown, produced or manufactured and/or from which services are provided. The origin of the goods must be determined according to the EU Customs Code or to the relevant international agreement applicable.

## Goods originating in the EU include goods originating in the Overseas Countries and Territories.

For the following equipment a derogation of the rule of origin has been granted and therefore these items can originate from any country:

| Lot | Spec No. | Equipment title |
| --- | --- | --- |
| 6 | 307 | Hardware and software upgrade for existing universal length machine |
| 9 | 317 | Air thermostat for standard resistors |
| 9 | 318 | Resistance bridge 1 mΩ to 100 MΩ, with Matrix Scanner |
| 9 | 329 | Precision LCR meter with calibration set |
| 9 | 334 | Rubidium clock with GPS comparison system and controller hardware and software |
| 9 | 369 | Upgrade of Electricity Meter Test Bench MTE 20 position to fit closed-link meters (3-phase CT's) and improved performance |
| 9 | 387 | Precision LCR meter |

Article 11	Performance guarantee

11.1	The amount of the performance guarantee shall be 10% of the Contract value and the sum for after sales service including any amounts stipulated in addenda to the Contract.

Article 12	Insurance

All supplies shall be fully insured for their full replacement value and associated expenses in accordance with international and Ghana law.

Article 17	Patents and licences

17.1	No derogation from Article 17 of the General Conditions is foreseen.

Article 18	Commencement order

18.1	The commencement date shall be the date of signature of the contract by both parties.

Article 19	Period of implementation of the tasks

19.1	Implementation of the tasks (delivery of supplies, installation, training) shall finish no later than 120 days after signature of the contract by both parties, except for the items with specification number 301 (lot 3) and specification number 318 (lot 9) for which the implementation period is 180 days.

Article 22	Amendments

22.2	The Contracting Authority reserves the right to vary by administrative order the quantities specified for all items in all lots by +/- 100 % at the time of contracting and during the validity of the Contract. The total value of the supplies may not rise or fall as a result of the variation of the quantities by more than 25 % of the tender price. The unit prices quoted in the tender will be multiplied by the revised quantities procured under the variation.

Article 26	General principles for payments

26.1	Payments shall be made in Euros.

Payments shall be authorised and made by the Ministry of Finance and Economic Planning, P. O. Box M40, Accra, and endorsed by the Delegation of the European Union in Ghana, P.O. Box 9505 KIA, Accra, Ghana. Phone: (+233) 21774202, Fax: (+233) 302774154.

26.5	In order to obtain payments, the Contractor must forward to the authority referred to in paragraph 26.1 above:

a)	if the pre-financing requested is equal or below EUR 300 000, unless no proof documents have been provided for the selection criteria or unless the Contracting Authority requires a financial guarantee following a risk assessment:

By derogation from article 26.5 of the General Conditions no pre-financing guarantee is required.

b)	For the 60 % balance, the invoice(s) [in triplicate] together with the request for provisional acceptance of the supplies.

By derogation, the pre-financing payment shall be made within 90 days from the date on which an admissible invoice is registered by the Contracting Authority. The final payment to the Contractor of the amounts due shall be made within 90 days following provisional acceptance of the goods, after receipt by the Contracting Authority of an admissible invoice.

26.9	The contract is at fixed price.

Article 28	Delayed payments

28.2	By derogation from Article 28.2 of the General Conditions, once the deadline laid down in Article 26.3 has expired, the Contractor will, upon demand, be entitled to late-payment interest in accordance with Article 28.2. The demand must be submitted within two months of receiving late payment.

Article 29	Delivery

29.3	The Contractor shall bear all risks relating to the goods until provisional acceptance at destination. The supplies shall be packaged so as to prevent their damage or deterioration in transit to their destination.

The packaging will become the property of the recipient subject to environmental considerations.

29.5/6/7	Supplies will be accompanied by set of documentation clearly written in English to cover the following but not be limited to (if applicable): installation manual; user manual; maintenance instructions; troubleshooting manual; applications manuals; a statement of performance characteristics, e.g., accuracy, sensitivity; health and safety information, etc

If so requested in the technical specifications, a calibration certificate should be provided.

Article 31	Provisional acceptance

The Certificate of Provisional Acceptance must be issued using the template in Annex C11.

Article 32	Warranty obligations

32.6	The commercial warranty is an extension of the factory and/or supplier warranty for an additional period of 24 months after the end of the standard warranty period referred to in Article 32.7. This warrant will be provided for the items specified in the technical specifications. The extended warranty will guarantee the reliability of the product under normal conditions of use. In case of malfunctioning of the equipment, the contractor will troubleshoot the problem within two working days after notification, overcome the problem  within a period of ten working days, and fully repair and re-integrate the equipment within a period of 20 working days. The contractor shall at its own costs repair and/or replace the defective equipment/parts. If repair/replacement of defective parts is no longer possible, the Contractor will replace the product within 30 working days. No extra costs will be borne by the Contracting Authority. The Contractor will also provide free of charge technical support, whether or not through a helpdesk function, to the user. Moreover, the Contractor will notify of and provide the user with free updates of firmware

32.7	The warranty must remain valid for one year after provisional acceptance.

Article 33	After-sales service

33.1	In the service and maintenance contract, for the items requested in the technical specifications, the Contractor will provide, apart from the services defined under the extended warranty, an annual site visit to inspect the product and implement a preventive maintenance programme, including cleaning, testing functionalities, and a status report of the product. If possible and available, the Contractor will remotely monitor the status and performance of the product. The last of the annual inspection visits will take place within three months before the end of the service and maintenance contract. The contractor will promptly perform on-site diagnostics and repairs after notification of malfunctioning of the product, if other solutions to solve the problem are of no avail. All costs related to labour and travel, and for replacement parts and components, will be included.  This service will be provided for 36 months after the date of provisional acceptance.

Article 40	Settlement of disputes

40.4	Any dispute arising out of or relating to this Contract which cannot be settled otherwise will:

(a)	in the case of a national contract, be settled in accordance with the national legislation of the state of the Contracting Authority; and

(b)	in the case of a transnational contract, be settled either:

(i)	if the parties to the Contract so agree, in accordance with the national legislation of the beneficiary country or its established international practices; or

- (ii)	by arbitration in accordance with the Procedural rules on conciliation and arbitration of contracts financed by the European Development Fund, adopted by Decision 3/90 of the ACP-EEC Council of Ministers of 29 March 1990 (Official Journal No L 382, 31.12.1990) (see Annex a12 to the Practical Guide to contract procedures for EU external actions).

- * * *